## Strategy Principles
Strategy Principles
By 2020 every carer should have appropriate opportunities to:
1. Access at the right time, the right type of information and advice for them, their family and the person they care for
2. Understand their rights and have access to an assessment
3. Have a voice for themselves and the person they care for
4. Have regular and sufficient breaks
5. Continue to learn and develop, train or work (if they wish to)
6. Look after their own health

## P1
Carers Strategy Action Plan
Principle 1: By 2020 every carer should have appropriate opportunities to access at the right time, the right type of information and advice for them, their family and the person they care for
Strategy Principle | What we need to do | Next steps (SMART actions) | Organisation | Who (person) | By when | Action updates: November 2018 - March 2019
1 | Information and advice available and accessible in different formats e.g. paper based, digital | Work with the Carers Centre (CC)/Sheffield Young Carers to ensure information on the carers service is up to date and in highly visible locations across Sheffield Teaching Hospitals (STH) locations, including the community directorate. | STH | Kerry Fenton-Coopland | 2018-10-01 | Leaflet developed and will be distributed to areas across the Trust. The next step will be to develop a support poster(s) to make the information more visible. Action to be carried forward to the STH Carers Project Group. September 2019 Not yet developed. For review.
|  | Home care providers will work with the Carers Centre/Sheffield Young Carers so that carers get the information they need either in hard copy or via a website. | SCC | Lee Teasdale-Smith | 2019-04-01 | Attended Home Care Provider Forum with Carers Centre 2018.
1 | Support for carers to navigate information | Work with the Carers Centre/Sheffield Young Carers to roll out the carer support volunteer programme so carers can be supported with the right information. | STH | Kerry Fenton-Coopland | 2018-08-01 | The role of Carer Volunteers did not materialise. The Sheffield Carers Centre plan to recruit a Volunteer to work with Stroke services at STH. The Volunteer role will support relatives and carers of patients who have had a stroke and advised what support is available to them. September 2019: Volunteer role in Stroke Outptaients commenced and going well.
|  | Home care providers have established referral/signposting processes to the Carers Centre/Sheffield Young Carers. This to be checked via contract monitoring/reviews. | SCC | Lee Teasdale-Smith | 2018-10-01 | This has been agreed and will now be monitored.
|  | GPs to have a carers lead. | SCCG | Eileen Hall | 2019-04-01 | Oct 2019 Carers comes under the Directorate of Out Of Hopsital Care - Clinical lead is sighted on the issues
|  | Provide information and access to support online | SYC | Laura Selby | 2019-09-01
|  | Better information about links between mental health services in schools and GPs | SCC | Carol Fordham | 2019-09-01
1 | Advice and guidance to support choices and maximise income (e.g. benefits and discounts) | Support the Carers Access Card scheme by offering carers a discount in Sheffield Teaching Hospitals cafes. | STH | Kerry Fenton-Coopland | 2018-10-01 | STH dining rooms have advised they cannot currentrly support the discount scheme. The Head of Commercial Development is discussing the scheme with the other retailers e.g. Boots/WHSmith at STH. Sep 2019: STH dining rooms now offer a 15% discout on production of Carers card. Discuount also offered by the coffee shops at NGH and RHH.
|  | Develop the Carers Card to provide carers with goods/services discounts across Sheffield. | CC | Pauline Kimantas | 2018-10-01 | 1,138 Carer Cards issued Dec-end Feb. 50 businesses signed up by end March. See action completed section
Can the Carers Card be used to raise awareness of employers caring responsibility?
1 | Information sharing between professionals, services and providers to avoid having to repeatedly tell the story | Explore carers passport options with the Carers Centre/Sheffield Young Carers. | STH | Kerry Fenton-Coopland | 2018-08-01 | STH Carers ID badge establish in 3 areas, if successful this will become available in more areas across the Trust. These are still being used in the 3 areas and will become more embedded with the Carers Volunteer Role. Sep 2019: Decision made at Carers Group to go with using the Carers card as the form of identification. Pilot to be agreed on Brearley 7 along with raising awareness campaign.
|  | Contact SPA re caring details captured on admission/assessment. | STH | Julie Whitaker
|  | Help the support services (like Parkinson's society) to understand how to contact adult social care. It's confusing and not clear at the moment. |  | ASC
Consistency of GP to avoid carers having to explain their situation repeatedly.
1 | Working with Primary Care to improve their knowledge regarding signposting | Pilot NHS England quality markers for GP surgeries through PCNs | SYC/CC/CCG/Healthwatch
|  | Write up good practice in GP surgeries - Southal & Beighton medical carer support & Handsworth surgery. | CC/ SYC
|  | Protected time for learning for GPs. | SHSC | Anita Winter
How to get the emphasis on GP referrals to CC on a par with flu. i.e. a must do.
|  | GPs getting consent from patients to forward their details to the Carers Centre. |  | Citywide register
|  | Link training to reception forums at neighbourhood (?). | CC | Sarah Chance
|  | Promote carer services at Practice Learning Initiative events | SCCG | Sarah Burt | 2018-05-01 | Oct 2019 CCG In Progress and ongoing
|  | Promote need to consider carer health / training / support within Multi-Disciplinary Team discussions | SCCG | Sarah Burt | 2018-10-01 | Oct 2019 CCG In Progress and ongoing
|  | Follow up actions on work started with GP practices to increase signposting/referrals to the Carers Centre | CC | Pauline Kimantas | 2018-10-01 | June- Sep Norwood Medical Centre has added a ‘Carers Centre’ page on their website and altered new patient registration form to invite carers to identify themselves and connect with Carers Centre services. Walkley House and Stannington medical centres received copy for their newsletter about carers’ support, as well as a line of text to be printed on prescriptions alerting carers to CC services. Publicity material has been sent to Meadowgreen Medical Centre, Dovercourt Surgery and The Hollies.
1 | Explore better links between agencies supporting families of young carers, to ensure good communication and information | Better links between Early Help and Social Care to ensure the needs of young carers and cared-for family members are met | SCC | CILs | Ongoing | Step-up step-down process now embedded and working well to support transition between MAST and Social Care.
|  | Explore how MAST and SYC work together, including Family project to ensure we are not duplicating work or overwhelming families | SCC/SYC | MAST/SYC | Ongoing | Apr-Dec 19: SYC promoted in MAST teams, and information about referral routes and SYC provision given to all MAST staff via Thresholds Of Need briefing sessions.
|  | Develop Sheffield Health and Social Care Trust guidance for confidentiality/data sharing with carers (based on South London and Maudsley Trust. | SHSCT | Jo Evans | 2019-09-01 | April-Oct 2019: Agnes attended SYC Action Group to get their input on this The Confidentiality and Information Sharing Guide will be taken to the SHSC Carers and Young Carers Strategy Implementation meeting on Tuesday 6th November for ratification and then will need to be signed by governance.
|  | Invite SCC First Point; a representative from Health & Wellbeing Board; a representative from Safeguarding board, and Carers & Young Carers Board to attend meetings. Create a diagram showing how different partners/boards relate and work together. | SHSCT | Emma/Frazer | Next Meeting
|  | Meet with Eileen Hall and Sarah Chance to take stock and review progress, plan further work, care navigation. | SC Centre & SYC
1 | Improve transitions for young adult carers and their families | Improving transitions between children’s and adult services (e.g. Ryegate) – ensure this is on transitions action plan too |  | 0-25 team | 2019-03-01 | There is ongoing work with services around transitions from children's to adults, this was one of the areas identified in the SEND inspection and so has been part of a working group. We are not at the end of the journey, but the transition pathways outlined below should go someway to hopefully bridge the gap, particularly with the emphasis on PFA., post 16 and ensuring children don't face the 'cliff edge' once they reach the end of statutory school age.
|  | CILS Specialists to 'Pathfind' (pilot) the Y4 Transition Pathway and Y9 Preparing for Adulthood pathway |  | RW &CILS | November 2018 onwards | This is an ongoing piece of work, there are 20 schools we are working with around the pathways of children who are transitioning on from primary to secondary and those who are leaving school. We have set up VLRs on those schools to correctly identify those children who are vulnerable and we are working on a tiered model to transitions, through whole school, curriculum, small group and individual support regarding transitions.
1 | Explore an online forum for young carers - signposting information and services. | Explore potential use of online resources for young adult carers | SYC | Laura Selby | Ongoing | April-Oct 19: First year of research completed - now looking into feasibility for providing 121 support sessions online for SYC members. (Research showed young people did not seem to want new apps or websites about caring). Kooth online counselling being promoted to all young people in SYC.
|  | SYC Action Group to look at how they can increase SYC’s online profile, including potential of Action Group social media account linked to SYC website, including idea of a mascot | SYC | Laura Selby | Ongoing | April-Oct 19: Ongoing use of SYC Twitter and Facebook for promotions (although some YP no longer using Facebook). Idea of mascot no longer being raised. Blogs written by Action Group, cared-for parents, SYC staff and people who were young carers who are now in professional roles being added to the SYC website. Comprehensive resources page on SYC for young people and professionals - continually updated. SYC have secured funding for a Digital Officer - currently recruiting to this post. Looking into feasibility for providing 121 support sessions online for SYC members.
|  | Develop intranet and external website, aligning with Carers Centre and SYC | ? | ? | ?

## P2
Carers Strategy Action Plan
Principle 2: By 2020 every carer should have appropriate opportunities to understand their rights and have access to an assessment
Strategy Principle | What we need to do | Next steps (SMART actions) | Organisation | Who (person) | By when | Action updates: November 2018 - March 2019
2 | Carer aware workforce – training for all frontline staff to recognise carers and the issues they face | Work with the Carers Centre / Sheffield Young Carers to arrange training for Sheffield Teaching Hospitals staff so they are more carer aware and know how to signpost/refer to the above organisations. This will include identifying Sheffield Teaching Hospitals’ staff who are caring. | STH | Kerry Fenton-Coopland | 2018-07-01 | Ongoing. Training currently scheduled for newly qualified nurses. September 2019: Moving and Handling training for young carers continues.
|  | Create carer awareness training e-learning package. | STH | Kerry Fenton-Coopland | 2018-10-01 | Action currently with the STH Carers Project Group. A number of existing online packages have been identified and the group will review these with a view to making them available for staff. September 2019: These are now available on STH PALMS system.
|  | Ensure care planning approaches include carers, carer health, contingency planning and carer Patient Activation measure | SCCG | Sarah Burt | 2018-10-01 | Oct 2019 In progress work being undertaken with Ageing Well Board and NHSE to include in PCSP developments in November 2019
|  | Work with clinical portfolios within the CCG to establish a baseline position re carer awareness | SCCG | Sarah Burt | 2018-04-01
|  | Work with HR team to highlight any needs re carer awareness and explore options | SCCG | Sarah Burt | 2018-10-01 | Oct 2019 Special Leave policy in place with dedicated section on Carer responsibilities
|  | Work with the Carers Centre/Sheffield Young Carers to arrange training for home care provider staff so they are more carer aware. | SCC | Lee Teasdale-Smith | 2019-01-01 | To be picked up at future home care provider forums.
|  | Carer awareness to be included in training for newly recruited home care provider staff. | SCC | Lee Teasdale-Smith | 2018-10-01 | This will need to be agreed on an individual provider basis. Ongoing.
|  | Include carer awareness refreshers as part of home care providers staff mandatory training. | SCC | Lee Teasdale-Smith | 2018-10-01 | To be picked up at future home care provider forums.
|  | Each home care provider to have a carers lead and carer champions whose remit is to raise carer awareness & represent carers | SCC | Lee Teasdale-Smith | 2018-10-01 | To be picked up at future home care provider forums.
|  | Ask volunteers at STH to raise awareness. Capture information. | STH | Julie Whitaker
|  | Deliver training to Sheffield City Council/Sheffield Teaching Hospitals/Clinical Commissioning Group (as a minimum) on an annual basis to ensure their staff are carer aware | CC | Pauline Kimantas | Ongoing | delivered presentations to Single Point of Access team based at NGH and at STH Best Practice Festival Met with team managers of Childrens Services to plan programme of sessions with staff about Carers Assessments. Attended Young Carers Project Schools network to talk about Carers Assessments. Presented to SCC Locality teams at Crystal Peaks about Carers Assessments. 2 x Carers Week Information sessions for ASC staff about Carers Assessments
|  | Carers Centre/Sheffield Young Carers to deliver 'link worker' training to SCC social work staff | CC/SYC/SCC (CILS) | Pauline Kimantas/ Laura Selby/Rose Ward | 2019-04-01 | Apr-Oct 19: COMPLETED but needs ongoing refreshers via the Link staff in their teams (Training delivered to Adult Social Care in July 2019 / CILS and Children's Fieldwork teams in autumn 18). Further ASC training booked for January 2019. Training delivered to CIL/ MAST / Children's Fieldwork but not Adult Social Care teams in November 2018. Action needed to train adult social care staff. YC Links will continue to run workshops as and when we feel a refresher for staff is needed (determined by Rose Ward and CILS team)
|  | Ensure volunteers are aware of carers register wherever they are. | Volunteering
|  | Develop training for SHSCT staff: understanding carers needs course; Carers assessment course; Guide for managers of staff who are carers, and posters promoting and supporting staff as carers | SHSCT | Joe Evans | 2019-06-01 | The pilot for the Carers’ Needs training will be delivered on Thursday 12th December 2019. There is a meeting scheduled for Tuesday 15th October 2019 for organising the Carers’ Assessment training. Poster for staff carers to be taken to the SHSC Carers and Young Carers Strategy Implementation meeting on Tuesday 6th November for ratification.
|  | Wider dissemination of info/training across all relevant sectors | ? | ? | 1 years time
|  | Make sure direct payments are offered as a first option, not as a last resort. | SCC | Elaine (ASC)
|  | Better support for direct payments. How can technology assist with payments/timesheets? | SCC | Sara to investigate
|  | Standardise practice amongst GP practices across the city. System Change. |  | CCG to discuss
Put a line on the bottom of subscriptions saying 'If you are a carer you can get support'.
|  | Factor Carers Centre into successful Neighbourhood Transformation Bids. | CCG/SCC | Sarah Chance, Emma Dickinson
Banking and finances: who can talk on someone's behalf when confidentiality is the barrier?
|  | Add caring responsibilities to EO form or recruitment at SYC. Explain that carers is a protected characteristic withing the Equality Act. | SYC
|  | Sharing good practice in schools. | Longley Park 6th Form
2 | Greater understanding by all agencies such as social care, health, education and housing staff about the rights of carers/ young carers | Host an information event on Sheffield Teaching Hospitals premises on Carers Rights Day. | STH | Kerry Fenton-Coopland | 2018-11-01 | Planned for 30/11/2019 - Unfortunately this did not occur but a communication was send out via STH Communications team about the day to raise awareness of Carers Rights. Plans are underway for the next carers rights day in June. Septemebr 2019: Has not happened. For reveiw by the Carers Group.
|  | Work with Sheffield Young Carers to promote carers rights during Carers Week and Carers Rights Day. | CC/SYC | Pauline Kimantas/ Sara Gowen | 2019-10-01 | Joint media pack and joint awareness poster produced and used widely on social media. April -Oct 19: SYC in Carers Week - held a large event for young carers and families, social media campaign/paper chain pledges successful - lots of pledges from SHSCT and other services, stall held in Debenhams, coordinated a meeting in Parliament with 7 other young carers services and MPs from around the country. Plans for Carers Rights Day not finalised yet
|  | Explore how to train young carers around employment rights. | SOHAS/SYC | Train employer's around carers rights
2 | Right to a young carers’ assessment and ensuring this is used effectively across the city. | YC Links Workers to hold regular meetings with their counterparts in Sheffield College to share information, identify training needs etc. | SCC | Rose Ward | 2019-03-01 | Not happening yet, but we are working on greater links into post 16 provision, this will form part of the discussion with Emma Beal in Life Long Learning - meeting planned for April.
|  | Closer monitoring by YC Link Workers of completion of Young Carers Assessment in order to improve quality control of completion – assessments to be run past link workers to support analysis of and next steps arising from each assessment | SCC | MAST (SYC to contact Louise Bower about this) | 2019-03-01
|  | Review of YCAs to continue | SCC | Lee Teasdale Smith / Carol Fordham | 2019-04-01 | The young carers assessment has been reviewed and there is a plan to integrate it into the My Plan document. The suggested amendments are still to be agreed so ongoing.
|  | Promote the use of Young Carers Assessments across education and employment settings. | SYC | Laura Selby |  | April-Oct 2019: Standing item at Young Carers Schools Network. Meetings held with new Young Carers Lead at Sheffield College. Training delivered to education and local authority staff from across the region via the university CPD annual conference. Following the meeting held in Westminster in June, SYC are liaising with Paul Blomfield MP to get follow up letters to Ministers asking whether the legislation is being enacted effectively.
|  | Ensure data collection and storage of young carers information and asesssments | SCC | Rose Ward and Richard Redman | Ongoing discussions | Look at how liquid logic can be developed to better identify and monitor Young Carers. Young Carers are still identifyable through ONE and CILS will continue to operate within this system.
|  | Establish a young carers register (see YC review) | SCC | Lee Teasdale-Smith | The preparation to start a register is nearly completed. The council needs Business Support resource in order to do the data entry, this is in the process of being agreed.
|  | Ensure we have accurate data. Fix current data problems | SCC | Elaine Howarth | 2019-06-01
2 | Support the development of mechanisms to ensure appropriate support is put in place and regularly reviewed following each young carers assessment. | Andy (SCC) meeting Steven tomorrow and will raise carer responsibilities whilst at school: teacher awareness. | Learn Sheffield | Steven Betts
|  | All identified young carers to be recorded and monitored on Premonitory (Sheffield College) and Cedar (Longley Park) so they can be tracked and offered support - with student's consent | Sheffield College / Longley Park | Hannah Dulieu / Vicky Bark | Ongoing | April -Oct 2019: SYC met with new lead Martin Tormey who is exploring where best to record young carers on their existing system. SYC have also created a young carer awareness training resource for Sheffield College tutor mentors to deliver to all students across the college
|  | Encourage schools to allow access to phones for young carers to reduce anxiety about the cared-for person at home (via YCSN, Learn Sheffield, Governors) | SYC | Laura Selby | 2019-04-01 | April - Oct 2019: Ongoing - On agenda for Dec YCSN meeting and SYC continue to raise at all relevant meeting and at their school governor training in January 2020
|  | Increase and measure monitoring of young carers on IYSS system | Sheffield Futures | John Moloughney | 2019-04-01

## P3
Carers Strategy Action Plan
Principle 3: By 2020 every carer should have appropriate opportunities to have a voice for themselves and the person they care for
Strategy Principle | What we need to do | Next steps (SMART actions) | Organisation | Who (person) | By when | Action updates: November 2018 - March 2019
3 | Communication campaign with multiple approaches including communities, primary care and hospitals to identifying carers and explaining the benefits of accessing help | Work with Carers Centre to agree a communications plan for Clinical Commissioning Group funded services | SCCG | Sarah Burt | 2018-10-01
|  | Work with the Carers Centre/Sheffield Young Carers to help them construct a communications plan to help identify more carers via home care providers. | SCC | Lee Teasdale-Smith | 2019-04-01 | to be agreed
|  | Home care providers to promote carers rights via communication campaigns during Carers Week and Carers Rights Day. | SCC | Lee Teasdale-Smith | 2019-04-01 | Carers Rights Day materials to be sent to home care providers for distribution.
|  | Support the development of the 'Carer Hub', the remit of which will be to give carers a voice on services across the city | SCC | Emma Dickinson | 2018-09-01
|  | Encourage / promote the use of the UCAS tick box for carers when it is implemented | SHU/UoS | Jade Bytheway / Sarah Adams | 2018-10-01 | Introduction of tick box delayed. Now estimated to be on the form in 2021 for students entering HE in 2022. In the meantime, UoS to continue to promote Disrupted Studies (specific to UoS) to all enquirers and applicants who disclose caring responsibilities. SHU: All applicants encouraged to disclose caring responsibilites to the SHU Progress Team - without a tickbox we depend upon partner networks (young carers charities and schools to refer young people) and actively update partners on our support and how to access it. The SHU admissions team also pass on all applications which mention an applicant is a carer (either in their personal statement or reference) the SHU Progress Team contact these applicants details of how we can support them through SHU Progress. Senior staff are aware of the delay to the tickboxes and the impact it has upon our work. April-Oct 2019: SYC have worked with SCC to ensure question about young carers is transferred from local UCAS Progress to new Sheffield Progress system for applying to post-16 education, so young carers can self-identify to their new education providers when they leave secondary school.
|  | Investigate why the texting pilot the Carers Centre did with a GP surgery wasn’t more successful. | SCCG | Eileen Hall | 2019-04-01 | Still investigating reasons - will update as soon as information available
|  | Raise home care issues at the home care provider forum. | CC | Pauline Kimantas | Attended home Care Forum 2018.
|  | Du'a Head Teacher's Blog. Meet with School Parliament linking to stress month | ? | Sara & Dawn | 2019-09-01
|  | Contact other Young Carer support charities such as Rotherham to work together. Continue to push the travel commissioner to get things going | SYC | Action Group | 2019-10-01 | April-Oct 19: Laura (SYC) and a young carer spoke at Rotherham Council Scrutiny Panel to share learning from travel and leisure card pilot in Sheffield. Meeting held in Westminster with 7 other young carers services. SYC coordinating a national youn gcarers voice meeting in Spring 2020.
|  | Explore online engagement of carers through Equality Hubs network | Equalities Hub | Rosie May | 2019-09-01
|  | Identify boards and representatives and feedback to Action Plan Group | SYC & SC Centre | ? | 2019-09-01
3 | Carers have a voice | Understand opportunities available within contracting process to highlight importance of carer voice within services and service development | SCCG | Sarah Burt | 2018-10-01 | Apr-Oct 2019: SYC Action Group took part in a consultation session about the city's new Mental Health Strategy. Feedback was shared by Andy Wallace with a range of other commissioners.
|  | Need more parent carers voices in plan and renew. Talk to Parent Carer Forum about the best way to engage | SCC | ? | 2019-09-01
|  | Get carers on all PPG in all 10 care networks. Push to carers and young carers to join PPG. | CC/SYC/CCG
|  | Make sure there is consistency of home support, as this is important to carers - they like to get to know the support workers. | HC/Forum/SCC
3 | Cared for people have a voice | SYC to explore new options for funding for information video/promotional materials for parents | SYC | Sara Gowen | 2019-03-01 | Apr-Oct 2019: Funding secured for 4 more years of family work at SYC. Focus since April has been on recruiting and inducting a new Community Engagement Worker to support cared-for parents into social/health activities in their communities. Plans to set up a parent steering group and possible parent film now underway.
|  | SYC to develop parents' voice in their service through parent networking events | SYC | Sara Gowen | 2019-03-01 | Apr-Oct 2019: As above
3 | Young carers have a voice | Explore involving young carers in the monitoring of Young Carer Assessments | SCC | Lee Teasdale-Smith | 2019-03-01 | No progress yet.
|  | SYC Action Group to continue to feed into the young carers action plan, via action plan refresh meetings | SYC | Laura Selby | Ongoing | April-Oct 2019: Consultation / planning meeting booked for 21st Oct
|  | Training the Trainers to be offered annually to SYC Action Group. Young carers to be invited to co-deliver or videos / case studies to be used where this is not possible | SYC | Laura Selby | 2019-03-01 | April-Oct 2019: 1 young carer spoke at SHSC quality improvement event. Training delivered in August 2019. Films and case studies always used in SYC training (average 1 workshop/presentation per week)
|  | Ensure young carer views guide the work of the SYC Young Carers Schools Network | SYC | Laura Selby | Ongoing | Ongoing: Young carers from host schools to be invited to attend and participate at every meeting (each half term) - no young carers were able to attend meetings in July or Oct 19
|  | Promote the role of Young Carers Reps on School Councils | SYC | Laura Selby | Ongoing | Ongoing: regularly raised at YCSN meetings
|  | Explore the potential for adult carers to mentor young carers, i.e. around transition | SYC & SC Centre | ? | 2019-09-01 | No progress to date
|  | Ensure all young carers have access to the preparation for adulthood conversation from the age of 14+. | Schools/LA Inclusion & Attendance Team
|  | Increase promotion of successful young carers voices and advocacy across the city | SYC | Action Group | 2019-10-01 | April-Oct 2019: 1 young carer spoke at SHSC quality improvement event. Planning for national voice/campaign network underway.

## P4
Carers Strategy Action Plan
Principle 4: By 2020 every carer should have appropriate opportunities to have regular and sufficient breaks
Strategy Principle | What we need to do | Next steps (SMART actions) | Organisation | Who (person) | By when | Action updates: November 2018 - March 2019
4 | Develop different ‘break’ options which are responsive to and reflect carers needs | Home care providers will deliver activities to support respite for carers, including, but not limited to, sitting services | SCC | Lee Teasdale-Smith | 2019-04-01 | The Council is currently looking at if home care providers can provide more intensive support to cover a carer break rather than the cared-for person having to go into residential respite.
|  | Develop the range of Time for a Break options | CC | Pauline Kimantas | 2018-10-01 | New options available from CarefreeBreaks; Merlin Entertainments. Details for new free hotel rooms offer being worked out. One carer has had 3 nights break through CareFeee breaks(April-June)
|  | Review of respite across the portfolio (take into account the confidence of respite for carers) | SCC | Lee Teasdale-Smith | 2019-10-01 | This paper is almost complete and will be going to the Senior Leadership Team and Portfolio Leadership Team before Christmas. The recommendations in the paper will hopefully improve the Council's approach to carer breaks.
|  | Flexible home support (a direct payment) who can respond to a stressed carer with flexi of around 10 hours a month to support the carer. | HS agencies being in and carer aware (?)
4 | Develop social assets and capital of carers e.g. ‘knit and natter’, sport activities, support groups, telephone befriending, buddies, local and national online forums / chat rooms | Work with home care providers to encourage them to refer/signpost to a range of community services that can benefit carers including the Carers Centre. | SCC | Lee Teasdale-Smith | 2019-04-01 | This will be developed and done via the home care provider forum.
|  | Co-produce carers wellbeing course (psycho-ed group) for carers of people with severe mental health problems. Expand wider in the future | SHSC | Joe Evans | 2019-09-01 | We are currently liaising with our Short-Term Education Programme (STEP) team with delivering the psychoeducational course for carers.
4 | Promote awareness about specialist funding available for young carers breaks (relates to overarching poverty theme) | MAST YC Links to continue to promote YCAF through their teams | SCC/CILs | YC Links | Ongoing
|  | Promote YCAF and other services such as Carers Card, SIV Plus One, card, cinema card, transport etc. | SYC / YC Links | Laura Selby / Rose Ward /YC Links | Ongoing | April-Oct 2019: Carers Card and Places for People leisure cards given to every new SYC member at initial home visits. Information about cinema card also given at home visit and range of discounts promoted via SYC Leavers Booklet. Carers Cards also being given out to young carers via schools who are members of SYC's schools network
|  | Continue to work with Louise Haigh MP on campaigning for free travel and discounted leisure passes on behalf of SYC | SYC | Laura Selby | Ongoing | April-Oct 19: See above for discount cards. SYC meeting Cllr Bob Johnson following Action Group's peititon to council for free travel.
|  | SYC to promote Young Carers Activity Fund before next round via emails and YCSN | SYC | Laura Selby | 2019-04-01 | April-Oct 19: SYC Action Group are trained and form the panel that administers the Young Carers Activity Fund 3 times per year to give other young carers access to respite. Following feedback from schools, this fund is now available for group applications as well as individual ones, in order to reach more young carers. Next panel - Oct 14th. Fund promoted in all SYC training and via email in advance of every closing date.
|  | All services to promote the fund to colleagues and young people in their services. Next closing date 8th Feb 2019 | All |  | 2019-04-01
|  | Continue to explore whether social prescribing can be extended to include children | SCC | Emma Dickinson | 2019-04-01 | April-Oct 19: Sheffield Futures have some funding for young people's social prescribing but SYC has not yet met with the new worker on this project
4 | Work with education providers to ensure young carers can access after-school / lunchtime activities / other activities to provide a break from caring. | Explore setting up more drop-ins for young carers at Longley College and in schools (to be promoted via the YCSN and by Action Group members in their own schools) to offer respite and peer support | Longley Park/SYC/Action Group | Laura Selby/Vicky Bark | 2019-04-01 | Ongoing: Several schools now offering drop ins for young carers or as part of Healthy Minds. Promoted regularly via YCSN.
|  | Check about exam support for young carers (some schools seem to offer additional time etc.) | SYC | Laura Selby | Ongoing | Apr-Oct2019: SYC checked with Learn Sheffield - schools have to make requests to individual exam boards for this.
|  | At least 5 young carers to attend the Routes Into Further Education university outreach event | TUoS/SHU/SYC | Sarah Adams/ Jade Bytheway/ Laura Selby | 2018-11-01 | April-Oct 2019: All outreach activities promoted widely to past and current SYC members. Some last minute drop out but 3 YC from SYC attended the summer school. SYC are part of HEPP implementation group for developing this year's outreach programme. SYC also promoted a University of Hull regional four-day young carers residential and 5 young carers from SYC attended.
|  | Send an email and set up a Facebook group for student carers at TUoS to raise awareness about support available and build peer support | TUoS |  | 2019-04-01

## P5
Carers Strategy Action Plan
Principle 5: By 2020 every carer should have appropriate opportunities to continue to learn and develop, train or work (if they wish to)
Strategy Principle | What we need to do | Next steps (SMART actions) | Organisation | Who (person) | By when | Action updates: November 2018 - March 2019
5 | Training and awareness for employers to understand carers needs and the benefits of having a diverse workforce and how flexible working can be used to retain staff. | Send out a questionnaire to 5 employers to understand how they identify and support carers. | CC | Pauline Kimantas | 2018-10-01 | Completed ( 15 mentors trained)
|  | Deliver 2 events (per year) for Sheffield employers to raise awareness of carers and the benefits that come from supporting them in the workplace. | CC | Pauline Kimantas | 2018-10-01 | Booked to deliver a presentation to Sheffield chamber of Commerce Health & Wellebing Forum and BeBraun.
|  | Support the development of the Sheffield Standard – This standard will support employers to be carer aware and have appropriate policies/processes in place to employ and retain carers in the workplace. | CC | Pauline Kimantas | 2019-04-01 | Work on the Sheffield Standard, led by the Council, has not progressed.
5 | Policies implemented to support adult and young carers to attend and achieve in their learning | Student carers at Sheffield Hallam University/University of Sheffield to be signposted to the Carers Centre. | SHU/UoS | Jade Bytheway/ Sarah Adams | 2018-10-01 | Any students who has disclosed their caring responsibilities, will be made aware of the Carers Centre. SHU: Any students who has disclosed their caring responsibilities, will be made aware of the Carers Centre for applicants to SHU this is done through the SHU Progress blog page for carers: https://blogs.shu.ac.uk/shuprogressblog/about-shu-progress/support-for-carers/?doing_wp_cron=1553004315.3316910266876220703125 contiuning for 2019-20
|  | Link with the Higher Education Progression Partnership to request carers support is advertised at the adult learners café | SHU/UoS | Jade Bytheway / Sarah Adams | 2018-10-01 | SHU: Higher Education Progression Partnership (Hepp) to confirm dates for adult learners’ café. HEPP is currently reviewing all provision and representatives from SHU and UoS are on the task and finish groups for adult learners and the vulnerable group learners. Still in planning stages cannot confirm what delivery will look like or what the targeting will be.
|  | CILS consultations about individual vulnerable children done in partnership with schools/partners to contain questions about caring responsibilities for children and their parents in the home | SCC | Rose Ward &CILS | Nov 18 onwards
|  | School attendance panels regarding irregular attendance to include discussions around caring responsibilities for adults and children in the family | SCC | Rose Ward &CILS | Nov 18 onwards
|  | Young carers to be named in all attendance and inclusion strategies/policies (including not penalising young carers by withholding attendance incentives when they cannot attend) | SCC | Rose Ward | 2018-11-01
|  | YC Links Workers to hold regular meetings with their counterparts in Sheffield College to share information, identify training needs etc. | SCC and Sheffield College | Rose Ward – CILs / Sheffield College | 2019-03-01
|  | See how we can facilitate carers to be volunteers. | STH | Julie Whitaker
|  | School governor awareness | Learn Sheffield | Andy to raise with Steven Betts
5 | Increase the identification of young carers in education and employment settings through training and awareness-raising to staff and pupils | SYC to do presentation at Governor's briefing and run training for Governors | SYC/Learn Sheffield | Laura Selby | 2019-04-01 | Apr-Oct 2019: Annual Governor training booked for Jan 2020
|  | Explore delivering young carer training on all PGCE courses, not just the post-16 course (now delivered annually on that course) | SYC/UoS/SHU | Laura Selby/Jade Bytheway/ Sarah Adams | 2019-04-01 | No progress
|  | Raise awareness about Young Carers School Network and Award with Alternative Providers | SCC 0-25 team | Nusrat Rehman | 2019-04-01
|  | Ensure young carers are well supported in new transition planning which is being developed / rolled out across schools (from Y4 and Y9) | CILS / SYC | Rose Ward | 2019-04-01 | This is linked in to all the work we completed with and in schools. This is also a linked discussion within the Primary and Secondary inclusion Panels.
|  | Explore getting caring/family health onto primary and secondary application forms and transition forms at YCSN meeting, at governor training and with Learn Sheffield | CILS / SYC | Laura Selby | 2019-04-01 | Apr-Oct 2019: Raised routinely at YCSN meetings and in all training delivered with schools. Template transition booklet (primary to secondary) available on SYC website for schools to support YCs transition. Question about caring responsibilities transferred on to new Sheffield Progress system for post-16 applications.
|  | Develop support offer for new arrivals with caring responsibilities and ensure they are linked into wider support in the city | SCC 0-25 team | Nusrat Rehman | 2019-04-01
|  | Adapt Community Youth Teams AssetPlus assessment to include questions re caring responsibilities | Sheffield Futures | John Moloughney | 2018-07-01
|  | SYC to deliver workshop at the annual Schools/University Conference | UoS/SHU/SYC | Laura Selby/Jade Bytheway/ Sarah Adams | 2019-04-01 | Conference took place at end of June 2019, Laura delivered a session which was well recieved - thank you Laura :)
|  | Training for Information Advice and Guidance team to give information about support for young carers through SYC, schools, colleges, universities, health services etc. | Sheffield Futures / UoS / SYC | John Moloughney/ Laura Selby/ Kate Smith | 2019-04-01 | No progress to date
|  | More student carers to be identified and then available to work as role models on outreach activities for young carers through newly added question about caring responsibilities on Ambassador recruitment forms | SHU | Jade Bytheway | Ongoing | We have recruited ambassadors from widening participation backgrounds including carers. We have also reviewed our recruitment process and have suggestions for improvements for the next recruitment cycle (September 2019). Hopefully these changes will provide us with more students from a range of backgrounds such as carers. We will also encourage applications from incoming first years who are supported by SHU Progress as carers. Recruitment is in progress but we hope to idenify carers, we have asked the on course support team to share the opportunity with carers.
|  | Train all student ambassadors on the definition and needs of young carers | SHU/UoS | Jade Bytheway/Sarah Adams | 2019-04-01 | SYC/SHU: All ambassadors who work with our team and wider department were trained on carers, care leavers and estranged students. The training discussed who are these groups and what challanges they face in coming to HE and how an ambassador can work effecitvely with these groups. Before any targeted inventions all ambassadors recieve a briefing remphaising the needs of the groups we work with e.g. carers. Due to changes in priorties we have delivered training to ambassadors which provides an overview of target groups, in future years would like to make it more detailed around carers (and the other most vulnerable students)
|  | Encourage school staff to check with family if young person's attendance is being affected by caring responsibilities (via YCSN meetings and CILS team) | SYC/CILS | Laura Selby/ Rose Ward | 2019-04-01 | SYC: On agenda for Dec YCSN
|  | Continue developing the new SHU Progress blog with information for young carers and other vulnerable groups | SHU | Jade Bytheway | Ongoing | Blog is live and has a page dedicated for carers. Each page on a topic e.g. accommodation/student finance has a section with specific info for carers too. Yes, blog has now ran for a full cycle and has been well recieved by students and provided them with relevant and timely information, advice and guidance. We will continue to use the blog for the next cycle of SHU Progress and ensure we talk about support and opportunities to carers.
|  | Explore having a regional index about young carer contacts / support available in all regional college with annual updates (similar to 'Propel' for care leavers) | HEPP / SHU | Jade Bytheway | 2019-04-01 | No Progress - This is being discussed as a potential piece of work in the vulnerable group task and finish group with HEPP. No Progress, meetings with HEPP are ongoing but it seems their priority is activity rather than online resource for VG.
|  | Get a carer tickbox added to Open Days booking form to sign post them to the SHU Progress stand | SHU | Jade Bytheway | 2010-10-01 | Trailed at the June Open day and was successful and has been extended onto the autumn open days
|  | Increase pastoral support (or awareness of it) in universities, not just financial support for students | UoS |  | 2019-04-01
|  | Training for dentistry students/access to dental course students | UoS/SYC | Sarah Adams/ Laura Selby | 2019-04-01 | SYC: No progress
|  | Check whether any students self-identified as carers on UCAS Progress this year and ensure systems are in place to follow this up with individual students this year and in the future | Longley Park | Vicky Bark | 2019-04-01
|  | Enhance the bursary offered to student carers at Longley Park based on what they most need and want (e.g. travel, additional payments, well-being support etc.) | Longley Park | Vicky Bark | 2019-04-01
|  | Fund travel for young carers for minimum one term, if not whole year | Longley Park | Vicky Bark | 2019-04-01
|  | Use the new question that has been added to bursary form about caring responsibilities to identify and offer support to young carers | Longley Park | Vicky Bark | 2019-04-01
|  | Offer all identified student carers a meeting with well-being staff to explore what support they need | Longley Park | Vicky Bark | 2019-04-01
|  | Young carers to ask their own schools / colleges about doing awareness raising activities for Carers Rights Day (30 Nov 18) and Young Carer Awareness Day (Jan 19). SYC to provide resources via YCSN and by request | Action Group / SYC | Actrion Group / Laura Selby | 2019-04-01 | Ongoing: '5 easy ideas' emails always sent to all SYC contacts. Also encouraged via YCSN meetings and Twitter. Action Group encouraged to plan/deliver activities in their schools.
|  | Explore increasing the identification and support for young carers across all campuses, including at Olive Grove | Sheffield College/SYC |  | 2019-04-01 | Apr-Oct 2019: SYC have created a young carer awareness training resource for Sheffield College tutor mentors to deliver to all students across the college
|  | Explore further first aid training sessions for new SYC groups | SYC/TUoS | Laura Selby / Sarah Adams | 2019-04-01 | Apr-Oct 2019: Delivered in May 2019, next course booked for May 2020
|  | Keep raising awareness about the new section on UCAS Progress where students can self identify as carers to their post-16 providers | SYC | Laura Selby | Ongoing | Apr-Oct 2019: System has changed from being called UCAS Progress to Sheffield Progress. SYC worked with council to ensure question about caring responsibilities transferred on to new system and adapted the question wording to make it clearer. Promoted at YCSN and all other training and meetings with schools/ other services.
|  | Get on the 'Head Teacher's Briefing' | SCC | Lee Teasdale-Smith & Michelle | 2019-10-01 | No progress.
|  | Take agenda to Learn Sheffield | SCC | Lee Teasdale-Smith | 2019-10-01 | No progress.
|  | Identify who could develop and implement the framework |  | Trading Standards, work training/skills board, Kris and other young people in Action Group | 2019-07-01 | SYC: no progress to date in terms of Action Group being contacted about this area of work
|  | How to share good practice amongst employers. Put on website. | SYC, Workpays
|  | Explore how to share employers for carers with SMES. | SCC, SMES | Lee & John
5 | Support the development of mechanisms to ensure appropriate support is put in place in schools, collegesand universities
|  | All identified young carers to be recorded and monitored on Premonitory (Sheffield College) and Cedar (Longley Park) so they can be tracked and offered support - with student's consent | Sheffield College / Longley Park | Hannah Dulieu / Vicky Bark | Ongoing
|  | Encourage schools to allow access to phones for young carers to reduce anxiety about the cared-for person at home (via YCSN, Learn Sheffield, Governors) | SYC | Laura Selby | 2019-04-01 | April - Oct 2019: Ongoing - On agenda for Dec YCSN meeting and SYC continue to raise at all relevant meeting and at their school governor training in January 2020
|  | Increase and measure monitoring of young carers on IYSS system | Sheffield Futures/SYC | John Moloughney | 2019-04-01
|  | Support more Sheffield schools and alternative providers to complete the Young Carers in Schools National Award | SYC | Laura Selby | Ongoing | Ongoing: SYC offers portfolio support sessions at the end of every YCSN meeting
|  | Explore holding careers workshops for young carers at school/university with alumni student carers | UoS |  | 2019-04-01
|  | Build on Education Exchange programme to include carers. Ensure volunteer opportunities and associated learning and training are promoted to carers. Work in partnership with Sheffield Libraries to ensure equality and equity in access to books, etc. | SHSC | ? | 2019-11-01
5 | Increased Young Carers Leads/Champions in education/employment settings who can be kept up to date with information | Increase participation in the SYC Young Carer Schools Network (YCSN) through ongoing recruitment through SYC contacts in schools, SYC training and through Learn Sheffield social media | SYC | Laura Selby | Ongoing | Ongoing - Current membership 88 schools and 5 alternative providers. Education Development Worker being recruited to increase SYC's capacity to work with schools (and other education providers).
5 | Involve young carers in the design and, where possible, delivery of training for education and employment settings | Enable young people to raise awareness about young carer issues in education settings (young trainers, peer mentors, school projects etc.) | SYC | Laura Selby | Ongoing | Training the Trainers offered annually to SYC Action Group - completed Aug 19 as part of wider Youth Social Action training course. Young carers invited to co-deliver or videos / case studies always used where this is not possible. Action Group developed peer mentoring training module which is available on YCSN members section of SYC website and promoted via YCSN meetings regularly.

## P6
Carers Strategy Action Plan
Principle 6: By 2020 every carer should have appropriate opportunities to look after their own health
Strategy Principle | What we need to do | Next steps (SMART actions) | Organisation | Who (person) | By when | Action updates: November 2018 - March 2019
6 | Training for health staff to recognise carers and understand the impact of caring on carers health and how to support them effectively | Work with Sheffield Carers Centre/Sheffield Young Carers to arrange training for Sheffield Teaching hospitals staff. | STH | Kerry Fenton-Coopland | 2018-07-01 | Ongoing. 11 SYC training sessions booked for newly qualified nurses 2019 - 2021. September 2019: Moving and handling training for young carers continues.
|  | Work with primary care commissioners to ensure practices are aware of and promote the Royal College of General Practitioners Supporting Carers programme | SCCG | Sarah Burt | 2018-10-01 | Ongoing - we can arrange for learning lunches and information to be circulated via comms bulletins
|  | GPs to update their registers so they know who the carer/young carer population is. | SCCG | Eileen Hall | 2019-04-01 | Oct 2019 Ongoing
|  | Health coaching awareness training with Carers Centre for advisors, etc. |  | Eileen Hall will liaise with with Lee, Ian and Nell in Carers Centre, and Sara at Young Carers | 2019-10-01
|  | Make sure home support agencies are aware of the importance of wellbeing, not just physical support. | HC provider/Forum/SCC
6 | Targeted health interventions for carers e.g. flu jab, carers check ups, screening programmes | Sheffield Teaching Hospitals staff to promote/give information on free annual carer health checks. | STH | Kerry Fenton-Coopland | 2018-07-01 | This will be done through signposting to SCC via the carers information leaflet. September 2019: For raising awareness pilot.
|  | Work with the Carers Centre to promote carer health checks | SCCG | Sarah Burt | 2018-10-01 | CCG Information has been provided to circulate in Surgeries to target those people with caring responsibilities .
|  | Home care providers to promote targeted health interventions to carers e.g. carers health check. | SCC | Lee Teasdale-Smith | 2018-10-01 | This will be developed and done via the home care provider forum.
|  | Feedback on how carers check-ups are being progressed at GP surgeries | SCCG | Eileen Hall | 2019-04-01 | Oct 2019 TBC - Will update before 30th October
|  | Alcohol/drug use for the cared for as a coping mechanism. | Andy to raise with DACT
|  | Discuss training around substance misuse. | SHSC, Jo/Victoria
|  | Gaming and gambling. Andy to raise with Public Health principle involved in gambling . | Magda Boo
Mental health first aid training could be a help for young carers.
Drugs & alcohol coping strategy. Burden on the person you care for if the carer is struggling. Prison: visits & difficulty.
6 | Awareness raising so carers understand their own health and wellbeing is important. Empowering carers with health conditions to self-manage their condition. | Signpost to NHS Choices carers webpage and other online resources e.g. health podcasts. | STH | Kerry Fenton-Coopland | 2018-10-01 | Explore options for information on STH website. - No progress on this but action to be carried forward to the STH Carers Project Group. September 2019: Discussions being held with STH Comms team for developemnt of an information for carers section on the website. SOme information available for staff carers on the Health and wellbeing intranet pages.
|  | Consider putting carer information in Good Health magazine. | STH | Julie Whitaker
6 | Flexible options for carers to access health appointments e.g. cannot attend same day appointment because cannot organise replacement care | GPs to try to be flexible when offering appointments to carers | SCCG | Eileen Hall | 2019-04-01 | In the North GPs don’t routinely change appointments just because someone is a carer, but they do adjust if asked. Once a person has expressed a different need they’ll make sure he/she gets the most appropriate appointment from then on.
6 | Put in place a rolling offer of free training to support young carers in their caring role based on young carers’ needs/views e.g. manual handling, mental health, first aid, cooking, managing finances – this should be informed by young carers. | Manual Handling Training to be delivered for young carers in SYC by Sheffield Teaching Hospitals | STH | Laura Selby | By August 2019 | First delivered 2018. STH have offered again this year - booked for June 19
|  | SYC offer training on range of relevant issues identified by young carers through their groups and 121s - ongoing | SYC | Laura Selby | Ongoing | Ongoing - including regular 121 and group wellbeing sessions, first aid (via UoS), manual handling via STH, online safety via SCC. Working with Door 43 and taking our 12+ age groups to their wellbeing cafe every half term to introduce them to the service.
|  | Explore how young carers can be involved with adult carers in the wellbeing courses being developed at the SHSC Trust | SHSC | Agnes Wozna | 2019-09-01 | Event held with Sheffield Young Carers on Thursday 8th August 2019 regarding Young Carer wellbeing. We are hoping for this to be an annual event.
|  | Young Carers Clinic | SHSC | Jo/Victoria
6 | Put in place a rolling offer of emotional wellbeing support for young carers and young adult carers
|  | SYC to engage young carers into Door 43 through termly visits to well-being café with 12-16 yr old groups / SYC staff to attend café and promote to 16-25 yr. olds six times per year | SYC/Sheffield Futures | Laura Selby / Emma Aley | Ongoing | Apr-Dec 2019: Taking SYC 12+ age groups to their wellbeing cafe every half term to introduce them to the service. New referral process now agreed between SYC and Door 43/Interchange to make it more accessible for young carers.
|  | Explore increasing availability or access into emotional health and well-being support for young adult carers who do not meet AMHS thresholds | Public health / CCG |  | 2019-04-01 | Apr-Dec 2019: SYC promoting Kooth online counselling to all members.
|  | Explore increasing capacity / frequency for well being cafes due to high demand | Public health / CCG |  | 2019-04-01
|  | Explore online counselling possibilities for young carers | SCC | Carol Fordham | 2019-04-01 | Awaiting Interchange to start their offer (Digitalk). SCC have commissioned a new online service - Kooth- for one year pilot from March 2019 - training on this for SYC team booked for May 19. Apr-Dec 2019: SYC promoting Kooth online counselling to all members.
|  | Communication while on CAMHS waiting list | CCG/SCC | Carol Fordham/CCG | 2019-04-01 | CAMHS representation on this group requested. SYC to offer staff training re. YCs to CAMHS once this happens.
|  | Co-production of carers wellbeing course (psycho-ed group) | SHSC | Jo Evans | 2019-12-01 | We are currently liaising with our Short-Term Education Programme (STEP) team with delivering the psychoeducational course for carers.
|  | Emotional supporter in schools; development of training/workshops in conjunction with carers | CCG, GPs, Practitioners Group, NIACE |  | No date specified
|  | Hold Sheffield wellbeing movement event in collaboration | SHSC | Jo Evans | 2019-12-01
|  | Young people who have been through CAMHS ebing trained as mentors to help young people currently going through CAMHS. | CAMHS mentors
6 | Explore relationships with GPs and awareness raising of young carer's issues and assessments, including young carer involvement in patient reference groups through GPs. | SYC / Carers Centre / CCG to continue exploring Carers Link Workers in GP surgeries | SYC/Carers Centre/CCG |  | 2019-04-01 | Apr-Dec 19: Some progress with individual GP surgeries, increased number with posters and information.
|  | SYC to explore with CCG about how to increase numbers of children being offered age-appropriate information from health professionals when family members get diagnosis and from OTs | SYC/CCG/ Public health |  | 2019-04-01 | No progress to date
|  | Write up a good practice example of a GP surgery supporting a young carer. To go on SYC website, publish through CCG News, and local medical committee | SYC/CCG | ? | 2019-09-01 | Apr-Dec 19: A good practice example has been gathered but not yet on website. SYC have promoted the upcoming NHS England quality markers for carer-friendly GP surgeries through CCG and local medical committee. Currently working on trialling the self-assessment tool in Sheffield.
|  | Investigate GP assessment to identify carers and also link to consent (GDPR) | CCG, GPs, Practitioners Group, NIACE |  | No date specified
|  | Challenges for the Board | CCG, GPs, Practitioners Group, NIACE |  | No date specified
|  | To inform GPs of all young carers we work with (with their consent). If and when we start working with a young carer, ask permission to inform their GP about them. | SYC
6 | Raise awareness within the health profession of young carers' needs and areas with which they may benefit from additional support. | Provide training / information sessions to CAMHS staff in identifying and supporting young carers, including importance of communication whilst on waiting list | SYC/CAMHS |  | 2019-04-01 | No progress to date
|  | Disseminate newly updated transitions protocol re. moving from CAMHS to adult mental health services (now also offering a monthly clinical interface meeting with AMH if there are issues with specific YP’s transition) | CAMHS |  | 2019-04-01
|  | SYC to explore with CCG about how to improve information and training from Occupational Therapists provided to young carers to help them carry out their caring roles safely | SYC/ CCG/ Public Health |  | 2019-04-01 | No formal progress to date. SYC did receive a call from an OT to ask about a child's caring responsibilities before discharging the cared for person - this is a good example of how different health services can identify and support young carers
|  | SYC to submit information to National Back Exchange professionals handbook | SYC |  | 2019-04-01 | Apr-Dec 19: No progress
|  | Sheffield Teaching Hospitals - getting Young Carer tick box added to Discharge forms and Admissions protocol | Carers Centre/SYC/ STH |  | 2019-04-01 | This has been progressed with the Carers Strategy Group - STH will give update
|  | Sheffield Teaching Hospitals - training for frontline staff re identifying YC (e.g. newly qualified nurses, A&E staff, diabetes and other specialist teams) | SYC/STH |  | 2019-04-01 | Apr-Dec 19: 11 SYC training sessions booked for newly qualified nurses 2019 - 2021. SYC emailed A&E contact to arrange training - no further progress
|  | Review and promote identification of young carers through PharmOutcomes with community pharmacies | SYC/Community Pharmacy Network |  | 2019-04-01 | Apr-Dec 19: SYC, SCC and Community Pharmacy Network met to look at how the PharmOutcomes system could be used to identify adult carers as well as young carers. No further progress due to ongoing issue with pharmacies negotiating their NHS contracts.
|  | Support and develop carers groups/forums across SHSC - including shared learning from RDASH | SHSC | Jo Evans | 2019-12-01 | There is ongoing work on supporting and developing carers groups and forums across SHSC.
6 | Raise awareness of the Young Carers' Assessment in health services in Sheffield | Explore a learning lunch to raise awareness of children as carers with the Clinical Commissioning Group (CCG) | SYC/CCG |  | 2019-04-01 | No progress to date
|  | Refresher training for substance misuse services regarding identifying YC | SYC |  | 2019-04-01 | Apr-Dec 2019: SYC on Hidden Harm Implementation Group and SYC delivered training to staff at Sidney Street and Fitzwilliam Centre.
|  | Explore ways to raise awareness about /involvement of young carers throughout SHSCT | SYC/SHSCT |  | 2019-04-01 | Apr-Oct 19: The Health and Social Care Trust Carers Strategy Group is now meeting regularly. Training for SHSCT staff planned for Dec 2019. SHSCT staff also delivered a Wellbeing day for young carers during the summer to help them learn more about specific mental health conditions and self-care -really successful - hoping to repeat/expand this in 2020.

## CP1
Carers Strategy Action Plan
Completed Principles
Principle 1: By 2020 every carer should have appropriate opportunities to access at the right time, the right type of information and advice for them, their family and the person they care for
Strategy Principle | What we needed to do | What we did (SMART actions) | Organisation | Who (person) | By when | Action update
| Advice and guidance to support choices and maximise income (e.g. benefits and discounts) | Sheffield Hallam University (SHU)/University of Sheffield (UoS) to give carers information about the Adult Dependants’ Grant and other higher education specific financial support. | SHU/UoS | Jade Bytheway / Sarah Adams | 2018-10-01 | New students entering UoS who have disclosed their recognised caring responsibilities will be contacted about the University bursary available to carers and how to apply. Existing students who disclose once at UoS or those who require further support have access to The Financial Support Team and/or Student Advice Centre to support choices and maximise income. SHU: All Carers who have disclosed their circumstances to SHU join the SHU Progress Support scheme. The scheme informs Carers of their financial entitlement such as the Adult Dependant Grants (we had an event on 7th March which discussed this in detail) and since this event we have published our guide to SFE on the SHU Progress blog (www.blogs.shu.ac.uk/shuprogressblog) which includes details of the grant. Furthermore, applicants who have caring responsbiliites are signposted to the Student Success Scholarship and as it becomes closer to September (and students transistioning to University) we will reinforce this message with details of how to access it. Furthermore, all carers are handed over to the Inclusive Suport team who will advertise the Student Success Scholarship to them once they enroll. Completed
| Working with Primary Care to improve their knowledge regarding signposting | Identify carers via the admissions process and then receive the carers information leaflet which will signpost carers to the Carers Centre and Sheffield Young Carers. | STH | Kerry Fenton-Coopland | 2018-10-01 | STH Complete - This is now added to electronic patient records system. Will review how many times it has been selected in 6 months time.
| Working with Primary Care to improve their knowledge regarding signposting | Add Carers Centre information onto the PRESS portal | SCCG | Sarah Burt | 2018-02-01 | Complete
| Working with Primary Care to improve their knowledge regarding signposting | Add link to referral documentation to Long Term Conditions review documentation | SCCG | Sarah Burt | Feb | Complete

## CP2
Carers Strategy Action Plan
Completed Principles
Principle 2: By 2020 every carer should have appropriate opportunities to understand their rights and have access to an assessment
Strategy Principle | What we needed to do | What we did (SMART actions) | Organisation | Who (person) | By when | Action update
| Carer aware workforce – training for all frontline staff to recognise carers and the issues they face | Carers Centre/Sheffield Young Carers to raise carer awareness via agenda slots / networking at the home care provider forum. | SCC | Lee Teasdale-Smith | 2018-10-01 | Completed
| Carer aware workforce – training for all frontline staff to recognise carers and the issues they face | Young carer case study and information handout to be included in all Thresholds of Need training | SYC | Laura Selby | 2019-04-01 | Completed
| Support the development of mechanisms to ensure appropriate support is put in place and regularly reviewed following each young carers assessment. | Continue offering training on the six week art programme and other resources for schools to use to support young carers via the Young Carers Schools Network (YCSN) | SYC | Laura Selby | Ongoing | Completed: Training offered after every YCSN meeting. Members only section now live on website with all SYC reousrces for schools (assemblies, lesson plan, art programme etc)

## CP3
Carers Strategy Action Plan
Completed Principles
Principle 3: By 2020 every carer should have appropriate opportunities to have a voice for themselves and the person they care for
Strategy Principle | What we needed to do | What we did (SMART actions) | Organisation | Who (person) | By when | Action update
| Involve young carers in the evaluation of the current local authority contract | Young carers contract to go out to tender for 2019 onwards | SCC | Carol Fordham | 2018-11-01
|  | Young Healthwatch, Chilypep and young carers to be involved in consultation re commission and retendering |  | Carol Fordham/SYC | 2018-11-01
| Communication campaign with multiple approaches including communities, primary care and hospitals to identifying carers and explaining the benefits of accessing help | All agencies to share what activities they are doing for Carers Week 2019 | All | All | 2019-06-01 | Completed
| Cared for people have a voice | Reducing stigma for families: SYC to provide campaign brief and cost; Carol Fordham to approach Director of Public Health | SYC/Carol Fordham | Sara Gowen / Carol Fordham | 2019-03-01 | COMPLETED /NOT POSSIBLE: Approached DPH, no funding available

## CP4
Carers Strategy Action Plan
Completed Principles
Principle 4: By 2020 every carer should have appropriate opportunities to have regular and sufficient breaks
Strategy Principle | What we needed to do | What we did (SMART actions) | Organisation | Who (person) | By when | Action update

## CP5
Carers Strategy Action Plan
Completed Principles
Principle 5: By 2020 every carer should have appropriate opportunities to continue to learn and develop, train or work (if they wish to)
Strategy Principle | What we needed to do | What we did (SMART actions) | Organisation | Who (person) | By when | Action update
| Policies implemented to support adult and young carers to continue to work for as long as they wish to | Sign up to Employers for Carers so SCC/STH and SME organisations can all benefit from this resource | SCCG | Lee Teasdale-Smith | Completed
| Increase the identification of young carers in education and employment settings through training and awareness-raising to staff and pupils | Share information/ training about young carers via the SHU staff school governor network | SHU/SYC | Jade Bytheway/ Sarah Adams | 2019-04-01 | Completed action.
| Increase the identification of young carers in education and employment settings through training and awareness-raising to staff and pupils | Have young carer awareness input during mentor training for ‘Us in Schools’ mentors in University of Sheffield | UoS/SYC | Laura Selby | 2019-04-01 | Completed ( 15 mentors trained)
| Increase the identification of young carers in education and employment settings through training and awareness-raising to staff and pupils | Have list of all school Young Carers Leads on SYC website so young carers and other professionals to know who to contact for information or support | SYC | Laura Selby | 2019-04-01 | Not possible to complete (due to GDPR)
| Support the development of mechanisms to ensure appropriate support is put in place in schools, collegesand universities | Continue offering training on the six week art programme and other resources for schools to use to support young carers via the Young Carers Schools Network (YCSN) | SYC | Laura Selby | Completed | COMPLETED: Training offered after every YCSN meeting. Members only section now live on website with all SYC reousrces for schools (assemblies, lesson plan, art programme etc)
| Increased Young Carers Leads/Champions in education/employment settings who can be kept up to date with information | Carers Centre/Sheffield Young Carers to deliver 'link worker' training to CILS staff | CC/SYC/SCC (CILS) | Pauline Kimantas/ Laura Selby/Rose Ward | Completed | Completed: SYC and Carers Centre training delivered to CILs team in November 2018. YC Links will continue to run workshops as and when we feel a refresher for staff is needed (determined by Rose Ward and CILS team)

## CP6
Carers Strategy Action Plan
Completed Principles
Principle 6: By 2020 every carer should have appropriate opportunities to look after their own health
Strategy Principle | What we needed to do | What we did (SMART actions) | Organisation | Who (person) | By when | Action update
6 | Ensure young carers remain a named group in the city's emotional wellbeing commissioning process and contracts | Young carers contract to be re-commissioned | SCC | Carol Fordham | Autumn 2018 | Young carers remain named group in EWB contract with Interchange.
| Raise awareness of the Young Carers' Assessment in health services in Sheffield | Provide training for health students at annual SHU conferences | SYC | Laura Selby | Completed | Completed: October 18 conference slot cancelled - no future dates planned
| Put in place a rolling offer of emotional wellbeing support for young carers and young adult carers | Explore ways to link more young adult carers into STEP 16-25 Transitions group | SHSC | Jo Evans | 2019-04-01 | SHSCT: STEP 16-25 Transitions workshop being held in April 2019: SYC invited. An event was held on Friday 26th April 2019 whereby young carers and representatives from 23 different services attended. This course has been renamed ‘STEP Forward’. Two workers from STEP also attended and facilitated a session at the Sheffield Young Carers event on the 8th August. A pilot course is due to start for 2 sessions a week for 4 weeks.